## Panel
ISPE Women in Pharma
Checklist - Panel Discussion - WIP Tool Kit
The following is the recommended checklist for preparing and conducting a panel discussion for Women in Pharma. This list can be modified to best suite specific panel discussions. Included in the checklist is a recommended T+/- days to assist in the planning, where T represents the day of the panel discussion. Where applicable, the name of the related sample document as well as a live link to the sample document is provided. File formats for samples include Microsoft Powerpoint, but are mostly in google document formats for easy collaboration, modification, and use.
Pre-Panel Discussion Checklist
Before the Panel Discussion, the following are recommended steps:
Done | Who | Step by Step | Recommended T +/- Days, T = Panel Discussion Date | Related Sample Document Name | Related Toolkit Document Link
| Organizer(s) | Review 5 Steps for a Great Panel | -22 | 5 Steps for a Great Panel | Five Steps to a Great Panel LinkedIn Article
| Organizer(s) | Decide on topic for panel discussion | -22
| Organizer(s) | Write a brief Abstract: title for the panel discussion, value proposition, brief paragraph description purpose/goals | -21 | Abstract | Panel Discussion Samples
| Organizer(s) | Identify potential moderator and panelists | -20 | Skills Matrix | Skills Matrix
| Organizer(s) | Identify available location/conference, date, and time | -19
| Organizer(s) | Write an invitation email to potential moderator and panelists. Include the brief Panel Discussion Narrative, proposed location/conference, date, and time | -19 | Invitation Email to Moderator and Panelists | Panel Discussion Invite and Thank You Templates
| Organizer(s) | Finalize panel discussion moderator and 4 panelists. Have at least 1 alternate | -18
| Organizer(s) | Write initial set of 4-6 questions for panel discussion (Consider including Moderator) | -18 | Questions | Panel Discussion Samples
| Moderator | Moderator holds 10-30 minute phone calls with each panelist separately to get to know them and review their answers to the questions and take notes and discover back stories/interesting nuggets of information (Consider including Organizer) | -17
| Moderator | Moderator finalizes questions for panel discussion | -15
| Organizer(s) | Convert to Standard WIP Bio Presentation Format | -14 | Bio Template | Panel Discussion Presentation Template
|  |  |  | Bio Sample | Panel Discussion Samples
| Organizer(s) | If not an ISPE International Event, like the local Affiliate/Chapter Events, then create a list of contact information for potential attendees with contact information including email address | -13
| Organizer(s) | If not an ISPE International Event, like the local Affiliate/Chapter Events, then write an invitation email to potential audience members | -12 | Invitation Email to Attendee | Panel Discussion Samples
| Organizer(s) | If not an ISPE International Event, like the local Affiliate/Chapter Events, then set-up all logistics for the room of the panel discussion | -12 | List of Logistics | Click on the Logistics Tab of this Document
| Organizer(s) | Ask Moderator and Panelists to post invitations on all social media channels and ask them to ask their professional network to re-post to their social networks | -12 | Social Media Post | Panel Discussion Samples
| Organizer(s) | Draft Panel Discussion Presentation (WIP Slides, Biographies, Panel Discussion Narrative, Agenda, Questions) | -11 | Panel Discussion Presentation | Panel Discussion Presentation Template
| Moderator | Facilitate conference with all Panelists ahead of time to discuss the biographies, content, re-review final questions, and the format of the session | -9
| Moderator or Organizer(s) | Facilitate conference call with organizer, and panelists ahead of time to write 1 Page Summary "Takeaways" for the panel discussion (Optional) | -9 | Key Takeaways | Panel Discussion Samples
| Organizer(s) | Finalize Panel Discussion Presentation (WIP Slides, Biographies, Panel Discussion Narrative, Questions) | -8 | Panel Discussion Presentation | Panel Discussion Presentation Template
| Organizer(s) | Write a hand-written Thank You Card to Moderators and Panelists to give each person at the session | -7 | Thank You Card | Panel Discussion Invite and Thank You Templates
| Organizer(s) | Verify all logistics/materials are ready for the room, 1 week prior to session | -7
| Organizer(s) | Verify all logistics/materials are ready for the room, 1 day prior to session | -1
| Organizer(s) | Verify all logistics/materials are ready for the room, early morning on the day of the panel discussion | 0
| Moderator, Organizer(s), Panelists | Moderator, Organizer, and Panelists meet ahead of time, possibly a few hours before panel discussion, to review expectations and format of the session | 0
| Moderator, Organizer(s), Panelists | Meet with moderator and panelists early, 30-45 minutes before the session is due to start. Hold a brief rehearsal, review the format of the session, and provide any last minute announcements | 0
Panel Discussion Checklist
During the Panel Discussion, the following are recommended steps:
| Organizer(s) | Collect attendee names and contact information | 0 | Attendee List | Panel Discussion List Templates
| Organizer(s) | Hand-out 1 Page Take-away | 0 | Key Takeaways | Panel Discussion Samples
| Organizer(s) | Assign a note taker to document notes and key takeaways from the panel discussion. After the panel discussion, provide suggestions to make future panel discussion sessions more successful | 0 | Notes, Takeaways, and Suggestions | Panel Discussion List Templates
| Organizer(s) | Deliver hand-written Thank You Card to Moderators and Panelists | 0 | Thank You Card | Panel Discussion Invite and Thank You Templates
| Organizer(s) | If not an ISPE International supported conference, demobilize room | 0
| Moderator | Present an opening statement to gain audience attention and create interest | 0
| Moderator | Introduce the panelists | 0
| Moderator | Ask questions to initiate discussion | 0
| Moderator | Balance communication among the panelists | 0
| Moderator | Keep the group on the agenda | 0
| Moderator | Summarize the discussion | 0
Post-Panel Discussion Checklist
After the Panel Discussion, the following are recommended steps:
| Organizer(s) | Transcribe all attendee names and contact information to an electronic Attendee List | 1 | Attendee List | Panel Discussion List Templates
| Organizer(s) | Send Thank You Email to attendees | 1 | Thank You Attendee Email | Panel Discussion Invite and Thank You Templates
| Organizer(s) | Add recommendations for improvements within 1 week of event | 5 | Comments, Questions, Recommendations, or Request | Post in Discussions in the Women in Pharma Online Community
Reference Documents
http://blog.addgene.org/how-to-5-steps-to-a-great-panel-discussion
http://www.scottkirsner.com/panels.htm

## Logistics
ISPE Women in Pharma® - Panel Discussion Resources
List of Logistics
The following is a list of logistics to consider. This list will change based on venue, size of group, and other variables.
General Checklist
Chairs for Panelists/Moderator
Small Tables
Hand-outs for Audience
Intro WIP Slide
Water for Panelists/Moderator
Notepad for Panelists/Moderator
Chairs for Audience
Lighting
Audio Visual and Technology Checklist
Microphone: Do you need a microphone for your speaker or microphones for audience questions?
Computer, data projector, screen: Will you need a computer and data projector and screen for the presentation. Who will provide equipment? Is the speaker bringing equipment, or are you responsible for providing?
Speakerphone: Is a speakerphone needed? Will anyone join the session via phone. Make sure there is a phone line and phone in the room.
Internet hook-up: Make sure you have the speed you need and the computer has the appropriate hardware and software to connect.
Technical issues and support: If you are using the hotel or conference to provide your equipment, do they have tech support on staff and what is their contact information? If not who will supply that help and for what cost. If you are using your own or borrowed equipment, can you handle technology problems that might arise?
Tips to Consider
Arrange panelists in a semi-circle so they can see eachother. Do not put panelists behind a table if avoidable.
Use a lower table, such as a coffee table, in front of panelists
Situate the moderator in middle of the panelists (not at a podium)
Place the audience as close as feasible to panelists
Provide panelists and moderator a microphone, preferrably a lapel style
Use just enough chairs for confirmed attendees. Add more if neeeded to avoid empty chairs.
Prepare with contingency plans, just in case... These could include weather, equipment failure, schedule changes, speaker cancellation, illness, or lateness.